## A3.1
Designated Entities Supplemental Validation (DESV) | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | A PCI DSS compliance program is implemented. | Req Id: | A3.1 | Cycle #: | 2024 | [7 empty] | 50% | 100% |  |  | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [7 empty] | 50% | 72.5% |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
|  |  |  | 86 | 71.67% | [10 empty] | Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Drafting a charter for a PCI DSS compliance program. | Atul Bhosale | 2025-01-31 | 4 | 100% | A3.1 | A3.1.1 | 1 | A3.1.1.a | 1 | Annual | Closed |  |  | PLAN | Q
DO | Defining a charter for a PCI DSS compliance program. | Atul Bhosale | 2025-02-28 | 8 | 100% | A3.1 | A3.1.1 | 1.1 | A3.1.1.a | 1 | Annual | Closed |  |  | DO
CHECK | Followup for PCI Charter Changes | Molly Brown | 2025-03-31 | 4 | 100% | A3.1 | A3.1.1 | 1.2 | A3.1.1.a | 1 | Annual | Open |  |  | CHECK
ACT | Obtain PCI Charter Approval from Executive Committee | Molly Brown | 2025-04-30 | 32 | 100% | A3.1 | A3.1.1 | 1.3 | A3.1.1.b | 1 | Annual | Open
PLAN | Drafting PCI DSS Annual Executive Summary | Atul Bhosale | 2025-09-30 | 6 | 100% | A3.1 | A3.1.1 | 1.4 | A3.1.1.c | 1.1 | Annual | Open |  |  | Open
DO | Submitting PCIDSS Annual Executive Summary | Atul Bhosale | 2025-10-31 | 12 | 45% | A3.1 | A3.1.1 | 1.5 | A3.1.1.c | 1.1 | Annual | Open |  |  | Closed
CHECK | Check for Updates in PCI DSS Annual Executive Summary | Warren Chang | 2025-11-30 | 8 | 0% | A3.1 | A3.1.1 | 1.6 | A3.1.1.c | 1.1 | Annual | Open
ACT | Obtain PCI DSS Annual Executive Summary Sign off | Bobby Ali | 2025-12-31 | 6 | 0% | A3.1 | A3.1.1 | 1.7 | A3.1.1.c | 1.1 | Annual | Open
PLAN | Definition of PCI DSS compliance activities including BAU | Atul Bhosale | 2025-03-31 | 6 | 100% | A3.1 | A3.1.2 | 2 | A3.1.1.c | 1.1 | Annual | Open
DO | Update PDCA Register with PCI Compliance Defined activities | Atul Bhosale | 2025-03-31 |  |  | A3.1 | A3.1.2 | 2.1 | A3.1.2.a | 1.2 | Annual | Open
DO | Assign Activities to PCI Security Team Members on MS Planner | Atul Bhosale | 2025-04-30 |  |  | A3.1 | A3.1.3 | 3 | A3.1.3.a | 1.2 | Quarterly | Open
CHECK | PCI Security Team Assignments Residual Risk report | Atul Bhosale | 2025-04-30 |  |  | A3.1 | A3.1.3 | 3.1 | A3.1.3.b | 1.3 | Quarterly | Open
CHECK | Monitor PCIDSS Activity Completion Times as per Frequency | Atul Bhosale | 2025-04-30 |  |  | A3.1 | A3.1.2 | 2.2 | A3.1.3.b | 1.2 | Daily | Open
ACT | Map PDCA with PCIDSS Priortized Approach file | Atul Bhosale | 2025-04-30 |  |  | A3.1 | A3.1.2 | 2.3 | A3.1.2.a | 1.4 | Quarterly | Open
PLAN | Design Annual PCI DSS assessment process | Atul Bhosale | 2025-04-30 |  |  | A3.1 | A3.1.2 | 2.4 | A3.1.2.a | 1.5 | Annual | Open
DO | Determine Annual Merchant Level | Atul Bhosale | 2025-12-31 |  |  | A3.1 | A3.1.2 | 2.5 | A3.1.2.a | 1.6 | Annual | Open
DO | BIA Report for potential PCI DSS impacts on Strategic business decisions | Atul Bhosale | 2025-11-30 |  |  | A3.1 | A3.1.2 | 2.6 | A3.1.2.a | 1.7 | Annual | Open | Mergers and acquisitions, new technology purchases, or new payment-acceptance channels
PLAN | Determine Roles for Assembled Security Awareness Team | Atul Bhosale | 2025-09-30 |  |  | A3.1 | A3.1.4 | 4 | A3.1.4.a | 1.8 | Annual | Open
DO | Mapping of PCI DSS Requirements to Different Roles, Materials, and Metrics | Atul Bhosale | 2025-05-31 |  |  | A3.1 | A3.1.4 | 4.1 | A3.1.4.a | 1.9 | Annual | Open
CHECK | Security Awareness Program Checklist | Atul Bhosale | 2025-06-30 |  |  | A3.1 | A3.1.4 | 4.2 | A3.1.4.a | 2 | Annual | Open | Appendix A https://listings.pcisecuritystandards.org/documents/PCI_DSS_V1.0_Best_Practices_for_Implementing_Security_Awareness_Program.pdf
ACT | Security Awareness Program Record | Atul Bhosale | 2025-07-31 |  |  | A3.1 | A3.1.4 | 4.3 | A3.1.4.b | 2.1 | Annual | Open | Appendix B https://listings.pcisecuritystandards.org/documents/PCI_DSS_V1.0_Best_Practices_for_Implementing_Security_Awareness_Program.pdf

## A3.2
Designated Entities Supplemental Validation (DESV) | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | PCI DSS scope is documented and validated. | Req Id: | A3.2 | Cycle #: | 2024 | [11 empty] | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [11 empty] | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Identify all payment channels (BPMNs)- includes Ingress, share, use, storage, Archive, Destroy |  |  |  |  | A3.2 | A3.2.1 | 5 | A3.2.1.a | 3 | Quarterly | Open |  |  | PLAN | Q
PLAN | Draft SOP For maintenance of NFD & DFD documentation |  |  |  |  | A3.2 | A3.2.1 | 5.1 | A3.2.1.a | 3.1 | Quarterly | Open |  |  | DO
DO | Asset Grouping in CDE, Security Impacting & Out-of scope Systems |  |  |  |  | A3.2 | A3.2.1 | 5.2 | A3.2.1.a | 3.2 | Quarterly | Open |  |  | CHECK
CHECK | Approval on the SOP For maintenance of NFD & DFD documentation |  |  |  |  | A3.2 | A3.2.1 | 5.3 | A3.2.1.a | 3.3 | Quarterly | Open |  |  | ACT
CHECK | CDE Segmentation Test Report including justification for environments being out of scope |  |  |  |  | A3.2 | A3.2.1 | 5.4 | A3.2.1.a | 3.4 | Quarterly | Open | Guidance-PCI-DSS-Scoping-and-Segmentation_v1.0 |  | CHECK
ACT | Update the Versioning & Changes to Network Diagrams |  |  |  |  | A3.2 | A3.2.1 | 5.5 | A3.2.1.a | 3.5 | Quarterly | Open |  |  | Open
ACT | Update the Versioning & Changes to Data Flow Diagrams |  |  |  |  | A3.2 | A3.2.1 | 5.6 | A3.2.1.a | 3.6 | Quarterly | Open
ACT | Data Discovery and Classification Tool Report |  |  |  |  | A3.2 | A3.2.1 | 5.7 | A3.2.1.a | 3.7 | Quarterly | Open
ACT | Consolidated Quarterly PCIDSS Scoping Review Report |  |  |  |  | A3.2 | A3.2.1 | 5.8 | A3.2.1.b | 3.8 | Quarterly | Open
ACT | PCI DSS impact assessment for all changes to systems or networks |  |  |  |  | A3.2 | A3.2.2 | 5.9 | A3.2.2.1 | 3.9 | Quarterly | Open
ACT | PCI DSS impact assessment for all changes to organizational structure |  |  |  |  | A3.2 | A3.2.3 | 5.9 | A3.2.3 | 3.9 | Quarterly | Open | Reassignments of personnel with responsibility for security control.
CHECK | Penetration testing Report covering all segmentation controls |  |  |  |  | A3.2 | A3.2.4 | 6 | A3.2.4 | 4 | Quarterly | Open
PLAN | Documention on Data Discovery and Classification Tool's Methodology |  |  |  |  | A3.2 | A3.2.5 | 5.7 | A3.2.5.b | 3.7 | Annual | Open
DO | Draft Response SOPs Upon detection of cleartext PAN outside the CDE |  |  |  |  | A3.2 | A3.2.5.2 | 6 | A3.2.5.2.a | 4.1 | Annual | Open
DO | Remediation Detailed Report Upon detection of cleartext PAN outside the CDE |  |  |  |  | A3.2 | A3.2.5.2 | 6.1 | A3.2.5.2.b | 4.2 | Annual | Open
PLAN | Documentation on DLP Mechanisms, Detecting & Generating audit logs and alerts |  |  |  |  | A3.2 | A3.2.6 | 6.2 | A3.2.6.a | 4.3 | Annual | Open
ACT | Documentation on Response SOPs For prompt investigation of alerts |  |  |  |  | A3.2 | A3.2.6.1 | 6.2 | A3.2.6.1.a | 4.4 | Annual | Open
ACT | Documentation on Response SOPs For Remediating DLP data leaks or process gaps |  |  |  |  | A3.2 | A3.2.6.1 | 6.3 | A3.2.6.1.b | 4.5

## A3.3
Designated Entities Supplemental Validation (DESV) | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | PCI DSS is incorporated into business-as-usual (BAU) activities. | Req Id: | A3.3 | Cycle #: | 2024 | [11 empty] | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [11 empty] | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Draft Policy & Procedures to promptly detect, alert, and address Critical Security Systems Failure |  |  |  |  | A3.3 | A3.3.1 | 7 | A3.3.1.a | 4.6 | Annual | Open |  |  | PLAN | Q
PLAN | Draft Response SOPs to Restoring security functions |  |  |  |  | A3.3 | A3.3.1.2 | 7.1 | A3.3.1.2a | 4.7 | Annual | Open |  |  | DO
DO | Generate audit trail Report for All Critical Security Systems Failures |  |  |  |  | A3.3 | A3.3.1.2 | 7.2 | A3.3.1.2.b | 4.8 | Quarterly | Open |  |  | CHECK
CHECK | Policy & Procedures to promptly detect, alert, and address Critical Security Systems Failure Signoff |  |  |  |  | A3.3 | A3.3.1.2 | 7.3 | A3.3.1.2.b | 4.9 | Quarterly | Open |  |  | ACT
ACT | Generate Remediation Detail Report for All Critical Security Systems Failures |  |  |  |  | A3.3 | A3.3.1.2 | 7.4 | A3.3.1.2.b | 5 | Quarterly | Open |  |  | Open
PLAN | Draft Policy & Procedures for Hardware and software technology Complaince (Req 2, 6, 12)Reviews |  |  |  |  | A3.3 | A3.3.2 | 8 | A3.3.2.c | 5.1 | Annual | Open | PCI DSS Reference: Requirements 2, 6, 12
ACT | Hardware and software technology Complaince Review Report for PCIDSS Req 2, 6, 12 |  |  |  |  | A3.3 | A3.3.2 | 7.5 | A3.3.3.a | 5.1 | Quarterly | Open
CHECK | Quarterly Evidence - Based Report for PCIDSS Req A3.2.2, A3.2.6, and A3.3.1 |  |  |  |  | A3.3 | A3.3.3 | 8.1 | A3.3.3.b | 5.2 | Quarterly | Open

## A3.4
Designated Entities Supplemental Validation (DESV) | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | Logical access to the cardholder data environment is controlled and managed. | Req Id: | A3.4 | Cycle #: | 2024 | [7 empty] | 100% | 45% |  |  | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [7 empty] | 100% | 100% |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
|  |  |  | 30 | 86.25% | [10 empty] | Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Draft User Account and Access Management Policy | IT Responder | 2025-10-31 | 12 | 45% | A3.4 | A3.4.1 | 9 | A3.4.1 | 6 | Half-Yearly | Open |  |  | DO
DO | Aggregate Users Account UNC Path, Means Granted & Permissions Report | IT Responder | 2025-02-28 | 8 | 100% | A3.4 | A3.4.1 | 9.1 | A3.4.1 | 6.1 | Half-Yearly | Open |  |  | CHECK
CHECK | Aggregate State-in-Time User Permissions in CDE, Connected-to & Out-of scope Systems | Overseer | 2025-03-31 | 4 | 100% | A3.4 | A3.4.1 | 9.2 | A3.4.1 | 6.2 | Half-Yearly | Open |  |  | CHECK
ACT | User accounts and access privileges Review Report for inscope system components | Atul Bhosale | 2025-09-30 | 6 | 100% | A3.4 | A3.4.1 | 9.3 | A3.4.1 | 6.3 | Half-Yearly | Open |  |  | Open

## A3.5
Designated Entities Supplemental Validation (DESV) | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | Suspicious events are identified and responded to. | Req Id: | A3.5 | Cycle #: | 2024 | [11 empty] | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [11 empty] | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Draft SOPs on Network Visibility strategy that includes signature based detection For CDE |  |  |  |  | A3.5 | A3.5.1 | 10 | A3.5.1a | 7 | Half-Yearly | Open |  |  | DO
PLAN | Draft SOPs on Network Visibility strategy that includes Rich protocol metadata For CDE |  |  |  |  | A3.5 | A3.5.1 | 10.1 | A3.5.1a | 7.1 | Half-Yearly | Open |  |  | CHECK
PLAN | Draft SOPs on Network Visibility strategy that includes File extraction & Analysis For CDE |  |  |  |  | A3.5 | A3.5.1 | 10.2 | A3.5.1a | 7.2 | Half-Yearly | Open |  |  | CHECK
PLAN | Draft SOPs on Network Visibility strategy that includes Full packet capture, For CDE |  |  |  |  | A3.5 | A3.5.1 | 10.3 | A3.5.1a | 7.3 | Half-Yearly | Open |  |  | Open
PLAN | Draft SOPs on Host Visibility strategy that includes Deployment of Data Collection Agents For CDE |  |  |  |  | A3.5 | A3.5.1 | 10.4 | A3.5.1a | 7.4 | Half-Yearly | Open
PLAN | Draft SOPs on Host Visibility strategy that includes Live Queries on Collected Data For CDE |  |  |  |  | A3.5 | A3.5.1 | 10.5 | A3.5.1a | 7.5 | Half-Yearly | Open
PLAN | Draft SOPs on Host Visibility strategy that enables centralized management of Data Collection Agents |  |  |  |  | A3.5 | A3.5.1 | 10.6 | A3.5.1a | 7.6 | Half-Yearly | Open
PLAN | Draft SOPs on Enterprise Visibility strategy that includes Intrusion detection honeypots |  |  |  |  | A3.5 | A3.5.1 | 10.7 | A3.5.1a | 7.7 | Half-Yearly | Open
PLAN | Draft SOPs on Suppression, threshold, customization and override of Detection Rule sets |  |  |  |  | A3.5 | A3.5.1 | 10.8 | A3.5.1a | 7.8 | Half-Yearly | Open
PLAN | Draft SOPs on Review and management of alerts generated by Detection Rules |  |  |  |  | A3.5 | A3.5.1 | 10.9 | A3.5.1a | 7.9 | Half-Yearly | Open
PLAN | Draft SOPs on Incident responses that integrates with Alerts & investigations of events |  |  |  |  | A3.5 | A3.5.1 | 11 | A3.5.1a | 8 | Half-Yearly | Open
PLAN | Draft SOPs to Extract summarized information on Incident observables |  |  |  |  | A3.5 | A3.5.1 | 11.1 | A3.5.1a | 8.1 | Half-Yearly | Open
DO | Deployment plan of Security Monitoring & Log Management Platform |  |  |  |  | A3.5 | A3.5.1 | 11.2 | A3.5.1b | 8.2 | Daily | Open |  |  | CHECK
DO | Incorporate Users, Roles & Grant Access to the Security Monitoring & Log Management Platform |  |  |  |  | A3.5 | A3.5.1 | 11.3 | A3.5.1b | 8.3 | Daily | Open |  |  | CHECK
DO | Install Agents as per SOPs to collect send host logs within CDE |  |  |  |  | A3.5 | A3.5.1 | 11.4 | A3.5.1b | 8.4 | Daily | Open |  |  | CHECK
DO | Customize all detection rules\as per SOPs within the CDE |  |  |  |  | A3.5 | A3.5.1 | 11.5 | A3.5.1b | 8.5 | Daily | Open |  |  | CHECK
ACT | Review and manage alerts as per SOPs on the Alerts Interface |  |  |  |  | A3.5 | A3.5.1 | 11.6 | A3.5.1b | 8.6 | Daily | Open |  |  | Open
ACT | Manage all detection rules as per SOPs within the CDE |  |  |  |  | A3.5 | A3.5.1 | 11.7 | A3.5.1b | 8.7 | Daily | Open
CHECK | Analyze PCAPs from network events within CDE |  |  |  |  | A3.5 | A3.5.1 | 11.8 | A3.5.1b | 8.8 | Daily | Open
ACT | Action Case Ids as per incident response SOPs and Update Audit Trail Report |  |  |  |  | A3.5 | A3.5.1 | 11.9 | A3.5.1b | 8.9 | Daily | Open
CHECK | Run Analyzers against case observables, to extract summarized information |  |  |  |  | A3.5 | A3.5.1 | 12 | A3.5.1b | 9 | Daily | Open
DO | Draft SOPs on Media Destruction for Electronic media with cardholder data in CDE | IT Leaders |  |  |  | 9.4.7 | 9.4.7 | 0.1 | 9.4.7a | 0.1 | Annual | Open
ACT | Approval on Media Destruction Policy & SOPs on Electronic media with cardholder data in CDE | Molly Brown |  |  |  | 9.4.7 | 9.4.7 | 0.2 | 9.4.7a | 0.2 | Annual | Open
CHECK | SOP Assessment Report for Media Sanitization/destruction for Electronic media with cardholder data in CDE | Sudip Mandal |  |  |  | 9.4.7 | 9.4.7 | 0.3 | 9.4.7b | 0.3 | Annual | Open

## M1
MILESTONE 1 | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | An accurate network diagram(s) is maintained that shows all connections between the CDE and other networks, including any wireless networks | Req Id: | 1.2.3 | Cycle #: | 2024 | [11 empty] | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [11 empty] | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Draft Network diagram(s) For CDE, All trusted networks, and all Untrusted Networks | IT Responder |  |  |  | 1.2 | 1.2.3 | 13 | 1.2.3.a | 9 | Annual | Open |  |  | DO
DO | Report on Locations, Network Segment Labelling, Out of Scope Labelling, legend or key information on NFDs | IT Responder |  |  |  | 1.2 | 1.2.3 | 13.1 | 1.2.3.b | 9.1 | Annual | Open |  |  | CHECK
ACT | Update the Versioning & Changes to Network Diagrams | IT Responder |  |  |  | 1.2 | 1.2.3 | 5.5 | 1.2.3.b | 3.5 | Annual | Open |  |  | CHECK
ACT | Approve the NFDs & their Versioning, Legends, Keys & Boundaries | IT Leaders |  |  |  | 1.2 | 1.2.3 | 13.3 | 1.2.3.a | 9.3 | Annual | Open |  |  | CHECK
CHECK | Verify All inScope, Connected to & Out of Scope Devices included in the NFDs | Overseer |  |  |  | 1.2 | 1.2.3 | 13.4 | 1.2.3.b | 9.4 | Annual | Open |  |  | Open
PLAN | Draft Data Flow diagram(s) For All Payment Channels & Process flows include Authorization, Capture, Settlement, Chargebacks, & Refunds | IT Responder |  |  |  | 1.2 | 1.2.4 | 13.5 | 1.2.4.a | 9.5 | Annual | Open
DO | Report on Data Sources Receipts & Transmissions for In-Scope/Connected-To/Out of Scope Assets in DFDs | IT Responder |  |  |  | 1.2 | 1.2.4 | 13.6 | 1.2.4.b | 9.6 | Annual | Open
ACT | Update the Versioning & Changes to Data Flow Diagrams | IT Responder |  |  |  | 1.2 | 1.2.4 | 5.6 | 1.2.4.b | 3.6 | Annual | Open
ACT | Approve the DFDs & their Versioning, Legends, Keys & Boundaries | IT Leaders |  |  |  | 1.2 | 1.2.4 | 13.8 | 1.2.4.b | 9.8 | Annual | Open
CHECK | Verify All inScope, Connected to & Out of Scope Devices included in the DFDs | Overseer |  |  |  | 1.2 | 1.2.4 | 13.9 | 1.2.4.b | 9.9 | Annual | Open
PLAN | Draft & Update The Company Wide Data Retention and Disposal Policy | Overseer |  |  |  | 3.2 | 3.2.1 | 14 | 1.2.5.a | 10 | Annual | Open
PLAN | Draft Data Retention and Disposal SOPs for MOTO Payment Channels | Overseer |  |  |  | 3.2 | 3.2.1 | 14.1 | 3.2.1a | 10.1 | Annual | Open
PLAN | Draft Data Retention and Disposal SOPs for Ecommerce Payment Channels | Overseer |  |  |  | 3.2 | 3.2.1 | 14.2 | 3.2.1a | 10.2 | Annual | Open
PLAN | Draft Data Retention and Disposal SOPs for Retail Payment Channels | Overseer |  |  |  | 3.2 | 3.2.1 | 14.3 | 3.2.1a | 10.3 | Annual | Open
DO | Draft & Submit SOP Audit Report of Data Retention & Disposal SOPs for All Payment Channels for Approval | Overseer |  |  |  | 3.2 | 3.2.1 | 14.4 | 3.2.1b | 10.4 | Annual | Open
CHECK | Approve SOP Audit Report of Data Retention & Disposal SOPs for All Payment Channels | Overseer |  |  |  | 3.2 | 3.2.1 | 14.4 | 3.2.1b | 10.5 | Annual | Open
ACT | Approve The Company Wide Data Retention and Disposal Policy & SOPs for All Payment Channels | Overseer |  |  |  | 3.2 | 3.2.1 | 14.5 | 3.2.1a | 10.6 | Annual | Open
PLAN | Draft Media Sanitization Standard Operating Procedure (SOP) based on (NIST SP 800-88 Guidelines) | Overseer |  |  |  | 3.2 | 3.2.1 | 14.6 | 3.2.1c | 10.7 | Annual | Open
DO | Draft & Submit Media Sanitization Standard Operating Procedure (SOP) Audit Report for Approval | Overseer |  |  |  | 3.2 | 3.2.1 | 14.7 | 3.2.1c | 10.8 | Annual | Open
ACT | Approve Media Sanitization Standard Operating Procedure (SOP) | Overseer |  |  |  | 3.2 | 3.2.1 | 14.8 | 3.2.1c | 10.9 | Annual | Open
CHECK | Approve Media Sanitization Standard Operating Procedure (SOP) Audit Report | Overseer |  |  |  | 3.2 | 3.2.1 | 14.9 | 3.2.1c | 11 | Annual | Open
PLAN | Draft Documentation for Payment Gateway Integration Configuration and Setup for Authorization process | IT Leaders |  |  |  | 3.3 | 3.3.1 | 15 | 3.3.1.a | 11.1 | Annual | Open |  |  | CHECK
DO | Approve Documentation for Payment Gateway Integration Configuration and Setup for Authorization process | Overseer |  |  |  | 3.3 | 3.3.1 | 15.1 | 3.3.1.b | 11.2 | Annual | Open |  |  | CHECK
ACT | Transaction Log Review Report for Authorization process to verify Cardholder name, PAN, Exp date, Service code is secured or Redacted | Overseer |  |  |  | 3.3 | 3.3.1.1 | 15.2 | 3.3.1.1 | 11.3 | Quarterly | Open |  |  | CHECK
ACT | Transaction Log Review Report for Authorization process to verify Card CVV Code is not Retained | Overseer |  |  |  | 3.3 | 3.3.1.2 | 15.3 | 3.3.1.2 | 11.4 | Quarterly | Open |  |  | CHECK
ACT | Transaction Log Review Report for Authorization process to verify Card PINs and PIN blocks is not Retained | Overseer |  |  |  | 3.3 | 3.3.1.2 | 15.4 | 3.3.1.2 | 11.5 | Quarterly | Open |  |  | CHECK
CHECK | Approve Log Review Reports for Authorization process | Overseer |  |  |  | 3.3 | 3.3.1.3 | 15.5 | 3.3.1.3 | 11.6 | Quarterly | Open |  |  | Open
PLAN | Draft Encryption Assessment Report for Sensitive Authentication Data prior to Authorization | Overseer |  |  |  | 3.3 | 3.3.2 | 16.1 | 3.3.2 | 11.7 | Annual | Open
DO | Compile findings in the Encryption Assessment Report | IT Responder |  |  |  | 3.3 | 3.3.2 | 16.2 | 3.3.2 | 11.8 | Annual | Open
ACT | Submit the Executive Summary on Encryption Assessment Report | IT Responder |  |  |  | 3.3 | 3.3.2 | 16.3 | 3.3.2 | 11.9 | Annual | Open
CHECK | Approve the Executive Summary on Encryption Assessment Report | IT Leaders |  |  |  | 3.3 | 3.3.2 | 16.4 | 3.3.2 | 12 | Annual | Open
PLAN | Draft Media Destruction Policy For Hard-copy materials with Cardholder data in CDE | Retail Leaders |  |  |  | 9.4 | 9.4.6 | 17 | 9.4.6.a | 12.1 | Annual | Open
DO | Draft SOPs on Media Destruction For Hard-copy materials with Cardholder data in CDE | Retail Leaders |  |  |  | 9.4 | 9.4.6 | 17.1 | 9.4.6.a | 12.2 | Annual | Open
ACT | Approval on Media Destruction Policy & SOPs For Hard-copy materials with Cardholder data in CDE | Overseer |  |  |  | 9.4 | 9.4.6 | 17.2 | 9.4.6.b | 12.3 | Annual | Open
CHECK | SOP Assessment Report for Media Sanitization/destruction For Hard-copy materials with Cardholder data in CDE | Overseer |  |  |  | 9.4 | 9.4.6 | 17.3 | 9.4.6.c | 12.4 | Quarterly | Open
PLAN | Draft Media Destruction Policy For Electronic media with cardholder data in CDE | IT Leaders |  |  |  | 9.4 | 9.4.7 | 18 | 9.4.7a | 12.5 | Annual | Open
DO | Draft SOPs on Media Destruction for Electronic media with cardholder data in CDE | IT Leaders |  |  |  | 9.4 | 9.4.7 | 18.1 | 9.4.7a | 12.6 | Annual | Open
ACT | Approval on Media Destruction Policy & SOPs on Electronic media with cardholder data in CDE | Overseer |  |  |  | 9.4 | 9.4.7 | 18.2 | 9.4.7a | 12.7 | Annual | Open
CHECK | SOP Assessment Report for Media Sanitization/destruction for Electronic media with cardholder data in CDE | Overseer |  |  |  | 9.4 | 9.4.7 | 18.3 | 9.4.7b | 12.8 | Annual | Open
PLAN | Identify all payment channels (BPMNs)- includes Ingress, share, use, storage, Archive, Destroy | Overseer |  |  |  | 12.5 | 12.5.2 | 5 | A3.2.1.a | 3 | Quarterly | Open | Information Supplement • Guidance for PCI DSS Scoping and Network Segmentation •
DO | Report on Data Sources Receipts & Transmissions for In-Scope/Connected-To/Out of Scope Assets in DFDs | IT Responder |  |  |  | 12.5 | 12.5.2 | 13.6 | 1.2.4.b | 9.6 | Annual | Open
DO | Asset Grouping in CDE, Security Impacting & Out-of scope Systems | Overseer |  |  |  | 12.5 | 12.5.2 | 5.2 | A3.2.1.a | 3.2 | Quarterly | Open
ACT | Update the Versioning & Changes to Data Flow Diagrams | IT Responder |  |  |  | 12.5 | 12.5.2 | 5 | 1.2.4.b | 3 | Annual | Open | Information Supplement • Guidance for PCI DSS Scoping and Network Segmentation •
ACT | Network zones Summary Report for Impact on PCIDSS Scope | IT Responder |  |  |  | 12.5 | 12.5.2 | 19 | 12.5.2.a | 12.9 | Annual | Open
ACT | Consolidated Annual PCIDSS Scoping Review Report | Overseer |  |  |  | 12.5 | 12.5.2 | 5.8 | 12.5.2.b | 3.8 | Quarterly | Open
CHECK | CDE Segmentation Test Report including justification for environments being out of scope | IT Responder |  |  |  | 12.5 | 12.5.2 | 5.4 | 12.5.2.b | 3.4 | Quarterly | Open
CHECK | Evaluate the security controls (e.g., firewalls, access control lists) implemented between zones | IT Responder |  |  |  | 12.5 | 12.5.2 | 19.2 | 12.5.2.b | 13.1 | Annual | Open
CHECK | Evaluate Network Topology Diagrams for TPSPs' Connections with access to CDEs | IT Responder |  |  |  | 12.5 | 12.5.2 | 19.3 | 12.5.2.b | 13.2 | Annual | Open
PLAN | Draft Media Destruction Policy For Electronic media with cardholder data in CDE | IT Leaders |  |  |  | 9.4.7 | 9.4.7 | 18 | 9.4.7a | 12.5 | Annual | Open
DO | Draft SOPs on Media Destruction for Electronic media with cardholder data in CDE | IT Leaders |  |  |  | 9.4.7 | 9.4.7 | 18.1 | 9.4.7a | 12.6 | Annual | Open
ACT | Approval on Media Destruction Policy & SOPs on Electronic media with cardholder data in CDE | Molly Brown |  |  |  | 9.4.7 | 9.4.7 | 18.2 | 9.4.7a | 12.7 | Annual | Open
CHECK | SOP Assessment Report for Media Sanitization/destruction for Electronic media with cardholder data in CDE | Sudip Mandal |  |  |  | 9.4.7 | 9.4.7 | 18.3 | 9.4.7b | 12.8 | Annual | Open

## M2
MILESTONE 2 | [12 empty] | ACT | PLAN |  |  |  | Total | Critical | High | Moderate | Low | Negligible
Description : | An accurate network diagram(s) is maintained that shows all connections between the CDE and other networks, including any wireless networks. (Update Frequency of Requirement assessment Tasks as per results recorded in PCI-Tk-id-70.0) | Req Id: | 1.2.3 | Cycle #: | 2024 | [11 empty] | Risk | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | Atul Bhosale | Updated: | 2024-01-01 | [11 empty] | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | CHECK | DO |  |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 0 |  |  |  |  | 0
Annual
PDCA phase | Activity Header | Owner | Due date | Activity time In Days | Completion % | Req# | Sub- Req# | Activity Id | Audit Test Id | DocId | Frequency | Status | Comments |  |  | M
PLAN | Compile List of Configuration Standards Benchmarks for All Inscope Assets | IT Responder |  |  |  | 2.2 | 1.2.1 | 20 | 1.2.1.a | 13.2 | Annual | Open |  |  | DO
DO | Execute Self Controls Security Assessment for All Inscope Assets | IT Responder |  |  |  | 2.2 | 1.2.1 | 20.1 | 1.2.1.a | 13.3 | Annual | Open |  |  | CHECK
ACT | Submit the CSA Report on Conformance of NSC rulesets for All Configuration standards defined in PCI-Doc-id-13.2 | IT Responder |  |  |  | 2.2 | 1.2.1 | 20.2 | 1.2.1.b | 13.4 | Annual | Open |  |  | CHECK
CHECK | Approve Conformance of NSC rulesets for All Configuration standards defined in | Overseer |  |  |  | 2.2 | 1.2.1 | 20.3 | 1.2.1.b | 13.5 | Annual | Open |  |  | Open
PLAN | Run an Nmap scan to determine open ports within the Inscope environment and which services are running. | IT Responder |  |  |  | 2.2 | 1.2.5 | 20.4 | 1.2.5.a | 13.6 | Annual | Open
PLAN | Draft SOPs for reviewing configurations of NSCs | IT Responder |  |  |  | 2.2 | 1.2.5 | 20.5 | 1.2.5.a | 13.7 | Annual | Open
DO | Compile the list of all allowed services, protocols, and ports For All Inscope & Connected-to Assets | IT Responder |  |  |  | 2.2 | 1.2.5 | 20.5 | 1.2.5.a | 13.6 | Annual | Open
ACT | Obtain & Maintain the business justifications and approvals for all allowed services, protocols, and ports | IT Responder |  |  |  | 2.2 | 1.2.5 | 20.6 | 1.2.5.a | 13.7 | Annual | Open
ACT | Compile the list of security features Defined to mitigate risk associated with insecure services, protocols, and ports in use | IT Responder |  |  |  | 2.2 | 1.2.6 | 20.7 | 1.2.6.a | 13.8 | Annual | Open
CHECK | Test Configuration settings for NSCs to verify that the defined security features for insecure services, protocols, and ports in use | Overseer |  |  |  | 2.2 | 1.2.6 | 20.5 | 1.2.6.b | 13.7 | Half-Yearly | Open
CHECK | Test Configuration settings for NSCs to verify that only approved services, protocols, and ports are in use | Overseer |  |  |  | 2.2 | 1.2.6 | 20.6 | 1.2.5.b | 13.7 | Half-Yearly | Open
CHECK | Review changes or updates to Configuration settings for NSCs | IT Responder |  |  |  | 2.2 | 1.2.7 | 20.7 | 1.2.7.b/c | 13.8 | Half-Yearly | Open
CHECK | Review Security & Consistency checks of Configuration files of NSCs with active network configurations | IT Responder |  |  |  | 2.2 | 1.2.8 | 20.8 | 1.2.8 | 13.9 | Half-Yearly | Open
PLAN | Define Restricting Inbound traffic to the CDE in Configuration Standards for NSCs | IT Responder |  |  |  | 2.2 | 1.3.1 | 21 | 1.3.1.a | 14 | Half-Yearly | Open
DO | Implement NSC rules that denies inbound traffic that is not specifically needed in CDE | IT Responder |  |  |  | 2.2 | 1.3.1 | 21.1 | 1.3.1.a | 14.1 | Half-Yearly | Open
ACT | Incorporate checks in the Firewall Audit checklist to Deny inbound traffic in CDE | IT Responder |  |  |  | 2.2 | 1.3.1 | 21.2 | 1.3.1.a | 14.2 | Half-Yearly | Open
CHECK | Collect System state against Firewall Audit Checklist to verify Deny inbound traffic in CDE | IT Responder |  |  |  | 2.2 | 1.3.1 | 21.3 | 1.3.1.b | 14.3 | Half-Yearly | Open
PLAN | Define Restricting Outbound traffic to the CDE in Configuration Standards for NSCs | IT Responder |  |  |  | 2.2 | 1.3.2 | 22 | 1.3.1.a | 14.4 | Half-Yearly | Open
DO | Implement NSC rules that denies Outbound traffic that is not specifically needed in CDE | IT Responder |  |  |  | 2.2 | 1.3.2 | 22.1 | 1.3.1.a | 14.5 | Half-Yearly | Open |  |  | CHECK
ACT | Incorporate checks in the NSC Audit checklist to Deny Outbound traffic in CDE | IT Responder |  |  |  | 2.2 | 1.3.2 | 22.2 | 1.3.1.a | 14.6 | Half-Yearly | Open |  |  | CHECK
CHECK | Collect System state against NSC Audit Checklist to verify Deny Outbound traffic in CDE | IT Responder |  |  |  | 2.2 | 1.3.2 | 22.3 | 1.3.1.b | 14.7 | Half-Yearly | Open |  |  | CHECK
PLAN | Define Restricting Wireless traffic to the CDE in Configuration Standards for NSCs | IT Responder |  |  |  | 2.2 | 1.3.3 | 23 | 1.3.3 | 14.8 | Half-Yearly | Open |  |  | CHECK
DO | Implement NSC rules that denies Wireless traffic that is not specifically needed in CDE | IT Responder |  |  |  | 2.2 | 1.3.3 | 23.1 | 1.3.3 | 14.9 | Half-Yearly | Open |  |  | CHECK
ACT | Incorporate checks in the NSC Audit checklist to Deny Wireless traffic in CDE | IT Responder |  |  |  | 2.2 | 1.3.3 | 23.2 | 1.3.3 | 15 | Half-Yearly | Open |  |  | Open
CHECK | Collect System state against NSC Audit Checklist to verify Denied Wireless traffic in CDE | IT Responder |  |  |  | 2.2 | 1.3.3 | 23.3 | 1.3.3 | 15.1 | Half-Yearly | Open
PLAN | Define NSCs between trusted & untrusted networks in Configuration Standards | IT Responder |  |  |  | 2.2 | 1.4.1 | 23.4 | 1.4.1.a | 15.2 | Half-Yearly | Open
DO | Include NSCs in Network Diagrams between trusted & untrusted networks | IT Responder |  |  |  | 2.2 | 1.4.1 | 23.5 | 1.4.1.a | 15.3 | Half-Yearly | Open
ACT | Evaluate Security posture of CDE with DMZ assessments | IT Responder |  |  |  | 2.2 | 1.4.1 | 23.6 | 1.4.1.b | 15.4 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist to verify NSCs implementation between trusted & untrusted networks | IT Responder |  |  |  | 2.2 | 1.4.1 | 23.7 | 1.4.1.b | 15.5 | Half-Yearly | Open
PLAN | Define publicly accessible services, protocols, and ports for Inbound traffic in NSC Configuration Settings | IT Responder |  |  |  | 2.2 | 1.4.2 | 24 | 1.4.2.a | 15.6 | Half-Yearly | Open
DO | Maintain On Demand State Table for communications initiated by system components in a trusted network. | IT Responder |  |  |  | 2.2 | 1.4.2 | 24.1 | 1.4.1.a | 15.7 | Half-Yearly | Open
ACT | Evaluate Security posture of trusted enviroments with State Table assessments | IT Responder |  |  |  | 2.2 | 1.4.2 | 24.2 | 1.4.1.b | 15.8 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist to verify Only Authorized Inbound Traffic within trusted network | IT Responder |  |  |  | 2.2 | 1.4.2 | 24.3 | 1.4.1.b | 15.9 | Half-Yearly | Open
PLAN | Define Antispoofing Control measures within trusted network in NSC Configuration Settings | IT Responder |  |  |  | 2.2 | 1.4.3 | 25 | 1.4.3 | 16 | Half-Yearly | Open
DO | Draft SOPs to implement Antispoofing Control measures within trusted network in NSC Configuration Settings | IT Responder |  |  |  | 2.2 | 1.4.3 | 25.1 | 1.4.3 | 16.1 | Half-Yearly | Open
ACT | Implement Antispoofing Control measures within trusted network in NSC Configuration Settings | IT Responder |  |  |  | 2.2 | 1.4.3 | 25.2 | 1.4.3 | 16.2 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist to detect and block forged source IP addresses within trusted network | IT Responder |  |  |  | 2.2 | 1.4.3 | 25.3 | 1.4.3 | 16.3 | Half-Yearly | Open
PLAN | Define system components storing cardholder data in DFDs & NFDs | IT Responder |  |  |  | 2.2 | 1.4.4 | 26 | 1.4.4.a | 16.4 | Half-Yearly | Open
DO | Draft SOPs for Control measures for restricting accessibility to System components that store cardholder data from untrusted network | IT Responder |  |  |  | 2.2 | 1.4.4 | 26.1 | 1.4.4.a | 16.5 | Half-Yearly | Open
ACT | Implement Control measures for restricting accessibility to System components that store cardholder data from untrusted network | IT Responder |  |  |  | 2.2 | 1.4.4 | 26.2 | 1.4.4.a | 16.6 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist validating restriction on access to System components that store CHD from untrusted network | IT Responder |  |  |  | 2.2 | 1.4.4 | 26.3 | 1.4.4.b | 16.7 | Half-Yearly | Open
PLAN | Define Methods to obscure IP addressing in NSC Configuration Settings | IT Responder |  |  |  | 2.2 | 1.4.5 | 26 | 1.4.5.a | 16.8 | Half-Yearly | Open
DO | Draft SOPs on Methods to obscure IP addressing (RFC 1918 or (RFC 4941) when initiating outgoing sessions to the internet | IT Responder |  |  |  | 2.2 | 1.4.5 | 26.1 | 1.4.5.a | 16.9 | Half-Yearly | Open
ACT | Implement Control measures for Methods to obscure IP addressing (RFC 1918 or (RFC 4941) when initiating outgoing sessions to the internet | IT Responder |  |  |  | 2.2 | 1.4.5 | 26.2 | 1.4.4.a | 17 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist to validate Methods to obscure IP addressing when initiating outgoing sessions to the internet | IT Responder |  |  |  | 2.2 | 1.4.5 | 26.3 | 1.4.4.b | 17.1 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist to restrict disclosure of internal IP addresses and routing information | IT Responder |  |  |  | 2.2 | 1.4.5 | 26.4 | 1.4.4.b | 17.2 | Half-Yearly | Open
PLAN | Draft endpoint security policy for computing devices, including company Devices or BYODs, that connect to both untrusted networks & the CDE | IT Responder |  |  |  | 2.2 | 1.5.1 | 26 | 1.5.1.a | 17.3 | Half-Yearly | Open
DO | Draft SOPs for host-based & network-based security control Measures for Devices that connect to both untrusted networks & the CDE | IT Responder |  |  |  | 2.2 | 1.5.1 | 26.1 | 1.5.1.a | 17.4 | Half-Yearly | Open
ACT | Implement host-based & network-based security control Measures for Devices that connect to both untrusted networks & the CDE | IT Responder |  |  |  | 2.2 | 1.5.1 | 26.2 | 1.5.1.a | 17.5 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist validating host-based & network-based security controls Devices connected to CDE | IT Responder |  |  |  | 2.2 | 1.5.1 | 26.3 | 1.5.1.b | 17.6 | Half-Yearly | Open
PLAN | Compile List of Configuration Standards Benchmarks for All Inscope Assets | IT Responder |  |  |  | 2.2 | 2.2.1 | 20 | 2.2.1.a | 13.2 | Half-Yearly | Open
DO | Draft SOPs for including New & Known Vulnerabilities within Configuration Standards for All Inscope Assets | IT Responder |  |  |  | 2.2 | 2.2.1 | 27 | 1.5.1.a | 17.6 | Half-Yearly | Open
ACT | Implement Configuration standards for new systems before or immediately after connected to a production environment. | IT Responder |  |  |  | 2.2 | 2.2.1 | 27.1 | 1.5.1.a | 17.7 | Half-Yearly | Open
CHECK | Collect System state against NSC Audit Checklist validating Configuration standards are implemented on all Inscope & Connected-to systems | IT Responder |  |  |  | 2.2 | 2.2.1 | 27.2 | 1.5.1.b | 17.8 | Half-Yearly | Open
PLAN | Draft SOPs for use of Multi-Factor Authentication (MFA) for all users & Administrators | IT Responder |  |  |  | 2.2 | 8.3.1 | 28 | 8.3.1.a | 17.9 | Half-Yearly | Open
PLAN | Develop IRP for responding to MFA-related security incidents | IT Responder |  |  |  | 2.2 | 8.3.1 | 28.1 | 8.3.1.a | 18 | Half-Yearly | Open
DO | Implement the process & Reporting for managing MFA devices, including registration, re-registration, and de-registration | IT Responder |  |  |  | 2.2 | 8.3.1 | 28.2 | 8.3.1.a | 18.1 | Half-Yearly | Open
ACT | Provide user support for MFA-related issues & Incident reports for Security Incidents | IT Responder |  |  |  | 2.2 | 8.3.1 | 28.3 | 8.3.1.b | 18.2 | BAU | Open
CHECK | Log Review Report to Monitor MFA usage and track any failed authentication attempts | IT Responder |  |  |  | 2.2 | 8.3.1 | 28.4 | 8.3.1.b | 18.3 | Half-Yearly | Open
PLAN | Draft Password Security policy all users & Administrators | IT Responder |  |  |  | 2.2 | 8.3.6 | 29 | 8.3.6 | 18.4 | Annual | Open
DO | Draft password complexity standard SOPs for all users & Administrators | IT Responder |  |  |  | 2.2 | 8.3.6 | 29.1 | 8.3.6 | 18.5 | Annual | Open
ACT | Implement password complexity requirements in AD/LDAP | IT Responder |  |  |  | 2.2 | 8.3.6 | 29.2 | 8.3.6 | 18.6 | Annual | Open
CHECK | Check and review password complexity requirements in AD/LDAP | IT Responder |  |  |  | 2.2 | 8.3.6 | 29.3 | 8.3.6 | 18.7 | Annual | Open
PLAN | Draft system configuration standards to include managing vendor default accounts | IT Responder |  |  |  | 2.2 | 2.2.2 | 30 | 2.2.2.a | 18.8 | Annual | Open
DO | Update & Approve system configuration standards on using vendor default accounts to verify accounts are implemented or removed | Overseer |  |  |  | 2.2 | 2.2.2 | 30.1 | 2.2.2.a | 18.9 | Annual | Open
ACT | Implement system administrator logging on using vendor default accounts to verify accounts are implemented | IT Responder |  |  |  | 2.2 | 2.2.2 | 30.2 | 2.2.2.b | 19 | Annual | Open
CHECK | Review system administrator logging & Vendor Documentation on using vendor default accounts to verify accounts are implemented | IT Responder |  |  |  | 2.2 | 2.2.2 | 30.3 | 2.2.2.b | 19.1 | Annual | Open
PLAN | Draft system configuration standards to include managing vendor default accounts | IT Responder |  |  |  | 2.2 | 2.2.2 | 30 | 2.2.2.a | 19.2 | Annual | Open | Security services, application and system accounts, point-of-sale (POS) terminals, payment applications, and Simple Network Management Protocol (SNMP) defaults.
DO | Update & Approve system configuration standards on using vendor default accounts to verify accounts are implemented or removed | Overseer |  |  |  | 2.2 | 2.2.2 | 30.1 | 2.2.2.a | 19.3 | Annual | Open
ACT | Implement system administrator logging on using vendor default accounts to verify accounts are implemented | IT Responder |  |  |  | 2.2 | 2.2.2 | 30.2 | 2.2.2.b | 19.4 | Annual | Open
CHECK | Review system administrator logging & Vendor Documentation on using vendor default accounts to verify accounts are implemented | IT Responder |  |  |  | 2.2 | 2.2.2 | 30.3 | 2.2.2.b | 19.5 | Annual | Open
PLAN | Draft Configurations in line with industry hardenening standards to Implement one primary function per server that require different security levels | IT Responder |  |  |  | 2.2 | 2.2.3 | 40 | 2.2.3.a | 19.6 | Annual | Open
DO | Implementing one primary function per server to prevent functions that require different security levels from co-existing on the same server | IT Responder |  |  |  | 2.2 | 2.2.3 | 40.1 | 2.2.3.b | 19.7 | Annual | Open
ACT | Report of Implemented Primary Functions, Security configurations for all On Prem/Virtual Server instances, containers to prevent Cross-Overs | IT Responder |  |  |  | 2.2 | 2.2.3 | 40.2 | 2.2.2.c | 19.8 | Annual | Open
CHECK | Examine, & confirm system settings to verify Security tiers, Server Roles & Features on Inscope Systems to avoid Cross-Overs | IT Leaders |  |  |  | 2.2 | 2.2.3 | 40.3 | 2.2.3.b | 19.9 | Annual | Open
PLAN | Draft Configurations Standards for Necessary services, protocols, daemons, and functions that can be enabled for Inscope Systems | IT Responder |  |  |  | 2.2 | 2.2.4 | 41 | 2.2.4.a | 20 | Annual | Open
DO | Implement Only Necessary services, protocols, daemons, and functions that can be enabled for Inscope Systems | IT Responder |  |  |  | 2.2 | 2.2.4 | 41.1 | 2.2.4.a | 20.1 | Annual | Open
ACT | Identify & Disable Unnecessary services, protocols, daemons, and functions that should not be enabled for Inscope Systems | IT Responder |  |  |  | 2.2 | 2.2.4 | 41.2 | 2.2.4.a | 20.2 | Annual | Open
CHECK | Examine, & confirm system settings to verify Only Necessary services, protocols, daemons, and functions are enabled alongwith their Approvals | Overseer |  |  |  | 2.2 | 2.2.4 | 41.3 | 2.2.4.b | 20.3 | Annual | Open
PLAN | Draft SOPs to scan for insecure services and protocols & Obtaining relevant Business justifications for their implementation | IT Responder |  |  |  | 2.2 | 2.2.5 | 42 | 2.2.5.a | 20.4 | Annual | Open
DO | Assess the risks associated with using insecure services, protocols, or ports, including potential vulnerabilities and misuse scenarios | IT Responder |  |  |  | 2.2 | 2.2.5 | 42.1 | 2.2.5.a | 20.5 | Annual | Open
ACT | Implement insecure protocols with justified business needs, and alternatives be explored | IT Responder |  |  |  | 2.2 | 2.2.5 | 42.2 | 2.2.5.a | 20.6 | Annual | Open
CHECK | Document the security features implemented and the justification for using the insecure protocol. | Overseer |  |  |  | 2.2 | 2.2.5 | 42.3 | 2.2.5.b | 20.7 | Annual | Open
PLAN | Draft configuration standards for applicable security parameters for Inscope Systems as per vendor documentation and industry Standards | IT Responder |  |  |  | 2.2 | 2.2.6 | 43 | 2.2.6.a | 20.8 | Annual | Open
DO | Compile List of Common security parameter settings for Inscope system components | IT Responder |  |  |  | 2.2 | 2.2.6 | 43.1 | 2.2.6.a | 20.9 | Annual | Open
ACT | On Demand Trainings & Guidelines on Common security parameter settings for Inscope system components | IT Responder |  |  |  | 2.2 | 2.2.6 | 43.2 | 2.2.6.b | 21 | Annual | Open
CHECK | Examine Accuracy & performance review of Common security parameter settings for Inscope system components | IT Leaders |  |  |  | 2.2 | 2.2.6 | 43.3 | 2.2.6.c | 21.1 | Annual | Open
PLAN | Draft Configuration Standards & SOPs for non-console Administrative access via browserbased interfaces and APIs | IT Responder |  |  |  | 2.2 | 2.2.7 | 44 | 2.2.7.a | 20.7 | Annual | Open
DO | Maintain administrator logs For non-Console Administrative Access To All-Inscope system components | IT Responder |  |  |  | 2.2 | 2.2.7 | 44.1 | 2.2.7.b | 20.8 | Annual | Open
CHECK | Examine & Review administrator logs For non-Console Administrative Access To All-Inscope system components | IT Responder |  |  |  | 2.2 | 2.2.7 | 44.2 | 2.2.7.b | 20.9 | Annual | Open
ACT | Maintain list of All Encrypted or UnEncryted Non console Accesses to All Inscope System Components | IT Responder |  |  |  | 2.2 | 2.2.7 | 44.3 | 2.2.7.c | 21 | Annual | Open
CHECK | Examine settings for system components and authentication services to verify Non Console Administrative Access | IT Responder |  |  |  | 2.2 | 2.2.7 | 44.4 | 2.2.7.d | 21.1 | Annual | Open
PLAN | Draft Wireless Access Policy for managing Wireless Access Configuration Settings including Change & Secure SNMP or wireless vendor defaults | IT Responder |  |  |  | 2.3 | 2.3.1 | 45 | 2.3.1.a | 21.2 | Annual | Open
PLAN | Draft SOPs for managing Wireless Access Configuration Settings including configuring SNMP or wireless vendor defaults, JML process & APNs | IT Responder |  |  |  | 2.3 | 2.3.1 | 45.1 | 2.3.1.a | 21.3 | Annual | Open
DO | Compile Vendor documentation & implement SOPs for managing Wireless Settings including configuring SNMP or vendor defaults & APNs | IT Responder |  |  |  | 2.3 | 2.3.1 | 45.2 | 2.3.1.b | 21.4 | Annual | Open
DO | Compile Vendor documentation & implement SOPs for managing Wireless Encryption keys for InScope systems connected to CDE | IT Responder |  |  |  | 2.3 | 2.3.2 | 45.3 | 2.3.2 | 21.5 | Annual | Open
CHECK | SOP Audit Report for system administrator logging into wireless devices to confirm compliance | IT Responder |  |  |  | 2.3 | 2.3.1 | 45.3 | 2.3.1.c | 21.5 | Annual | Open
ACT | Approve & Update SOPs for managing Wireless Access Configuration Settings | IT Leaders |  |  |  | 2.3 | 2.3.1 | 45.4 | 2.3.1.c | 21.6 | Annual | Open
PLAN | Develop and maintain detailed policies and procedures to ensure the secure transmission of PAN over open, public networks | IT Responder |  |  |  | 4.2 | 4.2.1 | 46 | 4.2.1.a | 21.7 | Annual | Open
DO | Use network and data flow diagrams to identify all points where PAN is transmitted or received over open, public networks. | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.1 | 4.2.1.a | 21.8 | Annual | Open
DO | Configure systems to use strong cryptography and secure protocols for transmitting PAN over open, public network | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.2 | 4.2.1.a | 21.9 | Annual | Open
DO | Regularly update and patch cryptographic software to maintain its strength and security. | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.3 | 4.2.1.a | 22 | Annual | Open
DO | Implement SOPs to regularly check against Certificate Revocation Lists (CRLs) or using Online Certificate Status Protocol (OCSP). | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.4 | 4.2.1.a | 22.1 | Annual | Open
CHECK | Ensure that the protocols in use support only secure versions or configurations & Diable fallbacks | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.5 | 4.2.1.b | 22.2 | Annual | Open
CHECK | Verify that the encryption strength based on checklist in accordance to NIST SP 800-52 and SP 800-57 | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.6 | 4.2.1.c | 22.3 | Annual | Open
CHECK | Regularly review and update the implementation based on new threats, vulnerabilities, and industry best practices. | IT Responder |  |  |  | 4.2 | 4.2.1 | 46.7 | 4.2.1.d | 22.4 | Annual | Open
ACT | Approve & Update SOPs for policies and procedures to ensure the secure transmission of PAN over open, public networks | IT Leaders |  |  |  | 4.2 | 4.2.1 | 46.8 | 4.2.1.b | 22.5 | Annual | Open
ACT | Train relevant personnel on policies and procedures on secure transmission of Primary Account Number (PAN) over open, public networks | IT Leaders |  |  |  | 4.2 | 4.2.1 | 46.9 | 4.2.1.d | 22.6 | Annual | Open
PLAN | Develop SOPs to compile a comprehensive inventory that includes all keys and certificates used to protect PAN during transmission | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47 | 4.2.1.1a | 22.7 | Annual | Open
PLAN | Develop a comprehensive inventory that includes all keys and certificates used to protect PAN during transmission | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.1 | 4.2.1.1a | 22.8 | Annual | Open
DO | For each key and certificate, record relevant information such as the algorithm, protocol, key strength, custodians, expiry dates, and the issuing CA | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.2 | 4.2.1.1b | 22.9 | Annual | Open
DO | Regularly update the inventory to reflect changes, such as new keys or certificates added, expired ones removed, or updates due to vulnerabilities | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.3 | 4.2.1.1b | 23 | Annual | Open
DO | Implement a system to track and alert for approaching expiry dates of keys and certificates to ensure timely renewal or replacement. | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.4 | 4.2.1.1b | 23.1 | Annual | Open
CHECK | Maintain & Approve the evidence of the inventory, such as screenshots, reports, or export files from key management systems, to demonstrate compliance | IT Leaders |  |  |  | 4.2 | 4.2.1.1 | 47.5 | 4.2.1.1b | 23.2 | Annual | Open
ACT | Assign specific individuals or teams the responsibility for maintaining the inventory and ensuring its accuracy and completeness. | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.6 | 4.2.1.1b | 23.3 | Annual | Open
ACT | Conduct regular training for staff involved in managing keys and certificates to ensure they are aware of policies, procedures, and best practices | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.7 | 4.2.1.1b | 23.4 | Annual | Open
ACT | Develop an IRP for instances when vulnerabilities are discovered in encryption software, certificates, or algorithms, including remediation | IT Responder |  |  |  | 4.2 | 4.2.1.1 | 47.8 | 4.2.1.1b | 23.5 | Annual | Open
PLAN | Determine which wireless networks are involved in transmitting Primary Account Number (PAN) or are connected to the CDE | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48 | 4.2.1.2 | 23.6 | Annual | Open
PLAN | Assess Current Cryptographic Standard used on networks determined in PCI-Tk-id-48.0 to identify any weaknesses or non-compliance issue | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.1 | 4.2.1.2 | 23.7 | Annual | Open
DO | Choose industry-recommended cryptographic protocols, like WPA3 or the latest TLS version for securing wireless communications | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.2 | 4.2.1.2 | 23.8 | Annual | Open
DO | Ensure that robust authentication methods (e.g., Extensible Authentication Protocol (EAP) with secure credentials) are in place for the wireless network. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.3 | 4.2.1.2 | 23.9 | Annual | Open
DO | Apply strong encryption to the transmission of data across the wireless network, ensuring that PAN and other sensitive data are encrypted. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.4 | 4.2.1.2 | 24 | Annual | Open
DO | Keep network devices updated to the latest firmware versions that support strong cryptographic standards | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.5 | 4.2.1.2 | 24.1 | Annual | Open
DO | Configure network devices to prevent fallback to weaker encryption standards or protocols that do not provide strong cryptography. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.6 | 4.2.1.2 | 24.2 | Annual | Open
DO | Consult and follow the specific documentation provided by network device vendors regarding cryptographic protocols and configurations | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.7 | 4.2.1.2 | 24.3 | Annual | Open
DO | Document the configurations and cryptographic standards implemented, including protocols and authentication mechanisms. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.8 | 4.2.1.2 | 24.4 | Annual | Open
CHECK | Regularly examine system configurations to verify compliance with the strong cryptography requirement. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 48.9 | 4.2.1.2 | 24.5 | Quarterly | Open
CHECK | Implement continuous monitoring to detect unauthorized access attempts or anomalies in wireless network traffic. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 49 | 4.2.1.2 | 24.6 | Quarterly | Open
CHECK | Regularly review and update the wireless network security measures in line with evolving industry best practices and standards. | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 49.1 | 4.2.1.2 | 24.7 | Quarterly | Open
ACT | Conduct training sessions for IT staff and users regarding the importance of strong cryptography in securing wireless networks | IT Responder |  |  |  | 4.2 | 4.2.1.2 | 49.2 | 4.2.1.2 | 24.8 | Quarterly | Open
ACT | Gather documentation, configuration files, and audit logs as evidence for compliance wireless networks are involved in transmitting PANs | Overseer |  |  |  | 4.2 | 4.2.1.2 | 49.3 | 4.2.1.2 | 24.9 | Annual | Open
PLAN | Create and maintain comprehensive policies and procedures addressing the secure transmission of PAN using end-user messaging technologies. | IT Leaders |  |  |  | 4.2 | 4.2.2 | 50 | 4.2.2.a | 25 | Annual | Open | E-mail, instant messaging, SMS, and chat
DO | Train employees & Regularly conduct awareness campaigns on the risks associated with sending PAN over end-user messaging technologies | Overseer |  |  |  | 4.2 | 4.2.2 | 50 | 4.2.2.a | 25.1 | Quarterly | Open
DO | Regularly examine and update system configurations to ensure alignment with latest security standards for encrypting data in transit | IT Responder |  |  |  | 4.2 | 4.2.2 | 50.1 | 4.2.2.b | 25.2 | Annual | Open
DO | Ensure that all third-party vendors providing messaging technologies are compliant with PCI DSS standards and use strong cryptography | IT Responder |  |  |  | 4.2 | 4.2.2 | 50.2 | 4.2.2.a | 25.3 | Annual | Open
ACT | Develop and implement an incident response plan for scenarios where cardholder data is received unsolicited via insecure channels | IT Responder |  |  |  | 4.2 | 4.2.2 | 50.3 | 4.2.2.a | 25.4 | Annual | Open
CHECK | Implement continuous monitoring mechanisms to detect and prevent unauthorized transmission of PAN. | IT Responder |  |  |  | 4.2 | 4.2.2 | 50.4 | 4.2.2.a | 25.5 | Daily | Open
ACT | Maintain an evidence set demonstrating adherence to documented policies, procedures, and system configurations in PCI-Tk-id-50.0 | Overseer |  |  |  | 4.2 | 4.2.2 | 50.5 | 4.2.2.a | 25.6 | Annual | Open
ACT | Implement Upgrades & robust patch management process to address vulnerabilities that could compromise the encryption of PAN during transmission | IT Responder |  |  |  | 4.2 | 4.2.2 | 50.6 | 4.2.2.b | 25.7 | Quarterly | Open
PLAN | Develop clear policies and procedures that outline how to identify and evaluate system components not at risk for malware | IT Responder |  |  |  | 5.2 | 5.2.3 | 60 | 5.2.3.a | 25.8 | Daily | Open
PLAN | Create and maintain a documented list of all system components deemed not at risk for malware, along with the rationale for each decision. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.1 | 5.2.3.a | 25.9 | Daily | Open
PLAN | Establish a process for the identification and evaluation of evolving malware threats, specifically targeting system components identified as not at risk. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.2 | 5.2.3.a | 26 | Daily | Open
DO | Periodically review the list of system components to confirm their status regarding malware risk aligned with the UA's risk management cycle. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.3 | 5.2.3.a | 26.1 | Daily | Open
DO | Develop Response plan to implement malware protection quickly and efficiently. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.4 | 5.2.3.a | 26.2 | Quarterly | Open
CHECK | Regularly monitor industry vulnerability alerts, security notices, and anti-malware forums to stay informed about evolving malware threats. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.5 | 5.2.3.c | 26.3 | Daily | Open
ACT | For each evaluation cycle, document the findings and the decision about whether each system component continues to not require anti-malware protection. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.6 | 5.2.3.c | 26.4 | Quarterly | Open
ACT | Ensure relevant personnel are trained on the policies and procedures for evaluating malware risks. | IT Leaders |  |  |  | 5.2 | 5.2.3 | 60.7 | 5.2.3.b | 26.5 | Quarterly | Open
ACT | Keep records & of all evaluations, decisions, and rationale for audit and compliance purposes. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.8 | 5.2.3.c | 26.6 | Quarterly | Open
ACT | Regularly update policies, procedures, and lists based on the latest evaluations and industry trends. | IT Responder |  |  |  | 5.2 | 5.2.3 | 60.9 | 5.2.3.c | 26.7 | Quarterly | Open
PLAN | Establish a clear, documented process that outlines how targeted risk analyses will be conducted. | GRC Responder |  |  |  | 12.3 | 12.3.1 | 70 | 12.3.1 | 26.8 | Annual | Open | TRA Process Includes the identification of assets, threats, likelihood and impact factors, and the justification for the chosen frequency
DO | Clearly identify and list all the assets being protected under each PCI DSS requirement. | GRC Responder |  |  |  | 12.3 | 12.3.1 | 70.1 | 12.3.1 | 26.9 | Annual | Open | Assets could include system components, data storage areas, and network segments, particularly those involved in the cardholder data environment (CDE)
DO | For each asset, identify the potential threats ranging from external threats like hacking and malware to internal threats like user error or unauthorized access | GRC Responder |  |  |  | 12.3 | 12.3.1 | 70.2 | 12.3.1 | 27 | Annual | Open
DO | Assess factors contributing to the likelihood and/or impact of each identified threat | GRC Responder |  |  |  | 12.3 | 12.3.1 | 70.3 | 12.3.1 | 27.1 | Annual | Open | This include factors like exposure to untrusted networks, system complexity, staff turnover, criticality of system components, or volume and sensitivity of data.
CHECK | Annual Review of Risk Analyses to ensure analyses stay current with any organizational changes, evolving threats, trends, and technologies. | GRC Responder |  |  |  | 12.3 | 12.3.1 | 70.4 | 12.3.1 | 27.2 | Annual | Open
ACT | Based on the risk analysis, determine and justify how frequently each requirement should be performed. | Overseer |  |  |  | 12.3 | 12.3.1 | 70.5 | 12.3.1 | 27.3 | Annual | Open
ACT | Conduct an enterprise-wide risk assessment (such as ISO 27005 or NIST SP 800-30) can help in understanding overarching risks and update the TRA | GRC Responder |  |  |  | 12.3 | 12.3.1 | 70.6 | 12.3.1 | 27.4 | Annual | Open
PLAN | Create an inventory of all system components within the organization's network for deploying Anti-Malware Solutions | IT Responder |  |  |  | 5.2 | 5.2.1 | 71 | 5.2.1.a | 27.5 | Quarterly | Open
DO | Install and configure anti-malware software on all identified system components | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.1 | 5.2.1.a | 27.6 | Quarterly | Open
DO | Periodic Evaluations of Exemptions for System components identified in PCI-Tk-id-60.1 | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.2 | 5.2.1.a | 27.7 | Annual | Open
DO | For any system components exempted from the anti-malware requirement, document the rationale and evidence supporting this decision. | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.3 | 5.2.1.a | 27.8 | Annual | Open
DO | Regularly update all systems and applications to protect against known vulnerabilities including keep the anti-malware software up-to-date. | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.4 | 5.2.1.a | 27.9 | Annual | Open
DO | Implement solutions that can detect anomalous behavior indicative of zero-day exploits, where malware exploits previously unknown vulnerabilities. | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.5 | 5.2.1.a | 28 | Annual | Open
CHECK | Collect evidence such as inventories, anti-malware deployment records, configuration settings, update logs, and documentation of periodic evaluations. | Overseer |  |  |  | 5.2 | 5.2.1 | 71.6 | 5.2.1.a | 28.1 | Annual | Open
ACT | Develop and maintain an incident response plan that includes procedures for responding to malware detections. | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.7 | 5.2.1.a | 28.2 | Annual | Open
ACT | Educate staff about the risks of malware, safe computing practices, and how to recognize potential malware activities. | IT Responder |  |  |  | 5.2 | 5.2.1 | 71.8 | 5.2.1.a | 28.3 | Annual | Open
PLAN | Choose anti-malware solutions that are comprehensive and capable of detecting a wide range of malware types | IT Leaders |  |  |  | 5.2 | 5.2.2 | 72 | 5.2.2 | 28.4 | Annual | Open
DO | Regularly examine the vendor documentation and configurations to ensure that the anti-malware solutions are up-to-date and configured | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.1 | 5.2.2 | 28.5 | Annual | Open
DO | Keep the anti-malware software and its malware definitions up to date | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.2 | 5.2.2 | 28.6 | Annual | Open
DO | Implement a layered defense strategy that includes network-based controls, host-based controls and endpoint security solutions. | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.3 | 5.2.2 | 28.7 | Annual | Open
DO | Employ advanced detection techniques such as sandboxing, privilege escalation controls, and machine learning algorithms to detect and respond | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.4 | 5.2.2 | 28.8 | Annual | Open
DO | Focus on preventing malware from entering the network through methods like email filtering, web filtering, and network segmentation. | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.5 | 5.2.2 | 28.9 | Annual | Open
DO | Implement strategies to contain and remove malware that does penetrate the network. | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.6 | 5.2.2 | 29 | Annual | Open
DO | Maintain a comprehensive set of evidence that demonstrates the effectiveness of the anti-malware solutions | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.7 | 5.2.2 | 29.1 | Annual | Open | This includes logs, reports from the anti-malware solutions, and records of updates and patches applied.
DO | Educate staff on recognizing potential malware threats and the importance of adhering to security policies. | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.8 | 5.2.2 | 29.2 | Annual | Open
CHECK | Continuously monitor the network and systems for signs of malware infection. | IT Responder |  |  |  | 5.2 | 5.2.2 | 72.9 | 5.2.2 | 29.3 | Daily | Open
CHECK | Conduct regular reviews and audits of the anti-malware strategies and tools to ensure they remain effective against current threats. | IT Responder |  |  |  | 5.2 | 5.2.2 | 73 | 5.2.2 | 29.4 | Annual | Open
ACT | Maintain a comprehensive set of evidence that demonstrates the effectiveness of the anti-malware solutions | IT Leaders |  |  |  | 5.2 | 5.2.2 | 73.1 | 5.2.2 | 29.5 | Annual | Open | This includes logs, reports from the anti-malware solutions, and records of updates and patches applied.
ACT | Educate staff on recognizing potential malware threats and the importance of adhering to security policies. | IT Responder |  |  |  | 5.2 | 5.2.2 | 73.2 | 5.2.2 | 29.6 | Annual | Open
PLAN | Conduct Targeted Risk Analysis (TRA) based on PCI-Tk-id-70.0, to identify system components not at risk for malware. | Overseer |  |  |  | 5.2 | 5.2.3.1 | 74 | 5.2.3.1 | 29.7 | Annual | Open
DO | Based on the TRA, define the frequency for periodic evaluations of the identified components. | IT Responder |  |  |  | 5.2 | 5.2.3.1 | 74.1 | 5.2.3.1 | 29.8 | Annual | Open
CHECK | Reevaluate the risk analysis & Periodic Evaluation process based on evolving malware threats | IT Responder |  |  |  | 5.2 | 5.2.3.1 | 74.2 | 5.2.3.1 | 29.9 | Annual | Open
ACT | Maintain a comprehensive set of evidence for Documented results of the periodic evaluations | IT Responder |  |  |  | 5.2 | 5.2.3.1 | 74.3 | 5.2.3.1 | 30 | Annual | Open
PLAN | Establish a centralized system for managing updates, automatically downloading updates, that can be tested before deployment of anti-malware solution | IT Responder |  |  |  | 5.3 | 5.3.1 | 75 | 5.3.1.a | 30.1 | Annual | Open
DO | Maintain documentation of the anti-malware solution's configuration settings, related to automatic updates validated in the master installation. | IT Responder |  |  |  | 5.3 | 5.3.1 | 75.1 | 5.3.1.a | 30.2 | Annual | Open
DO | Implement monitoring mechanisms to alert the IT team if an update fails or if a system component is not using the latest malware definitions. | IT Responder |  |  |  | 5.3 | 5.3.1 | 75.2 | 5.3.1.a | 30.3 | Annual | Open
CHECK | Regularly examine system components and logs to ensure that the anti-malware solutions and definitions are current and have been deployed promptly. | IT Responder |  |  |  | 5.3 | 5.3.1 | 75.3 | 5.3.1.b | 30.4 | Weekly | Open
ACT | Collect evidence sets such as configuration settings, logs showing successful update installations, and records of update schedules. | IT Responder |  |  |  | 5.3 | 5.3.1 | 75.4 | 5.3.1.b | 30.5 | Quarterly | Open
ACT | Ensure that Auto-update process covers all necessary security updates, signatures, threat analysis engines, and other malware protections. | IT Responder |  |  |  | 5.3 | 5.3.1 | 75.5 | 5.3.1.a | 30.6 | Annual | Open
PLAN | Maintain documentation that includes regarding anti-malware solution configuration settings, logs, scan results, and evidence of real-time protection. | IT Leaders |  |  |  | 5.3 | 5.3.2 | 76 | 5.3.2.a | 30.7 | Annual | Open
DO | Schedule scans at regular intervals (e.g., daily, weekly) and should cover all system components within the Cardholder Data Environment (CDE). | IT Responder |  |  |  | 5.3 | 5.3.2 | 76.1 | 5.3.2.a | 30.8 | Quarterly | Open
DO | Configure the anti-malware solution to ensure enabling real-time protection features. | IT Responder |  |  |  | 5.3 | 5.3.2 | 76.2 | 5.3.2.a | 30.9 | Annual | Open
DO | Integrate the anti-malware solution with firewalls, IDS, SIEMs and other security systems. for comprehensive protection. | IT Responder |  |  |  | 5.3 | 5.3.2 | 76.3 | 5.3.2.a | 31 | Annual | Open
DO | Ensure the anti-malware solution covers all critical areas, including mail servers, browsers, and instant messaging software often entry points for malware. | IT Responder |  |  |  | 5.3 | 5.3.2 | 76.4 | 5.3.2.a | 31.1 | Annual | Open
CHECK | Implement procedures for reviewing and interpreting scan results & logs to ensure timely responses to any identified threats. | IT Leaders |  |  |  | 5.3 | 5.3.2 | 76.5 | 5.3.2.b | 31.2 | Quarterly | Open
ACT | Regularly review and update the anti-malware solution to adapt to evolving threats by updating definitions, reconfiguring scan intervals, & adjusting scope. | IT Responder |  |  |  | 5.3 | 5.3.2 | 76.6 | 5.3.2.b | 31.3 | Quarterly | Open
PLAN | Perform a TRA to evaluate risks associated with malware in the entity's environment. | Overseer |  |  |  | 5.3 | 5.3.2.1 | 80 | 5.3.2.1.a | 31.4 | Quarterly | Open
DO | Based on the TRA, determine an appropriate frequency for conducting malware scans. | IT Responder |  |  |  | 5.3 | 5.3.2.1 | 80.1 | 5.3.2.1.a | 31.5 | Quarterly | Open
CHECK | Prepare a comprehensive evidence set that includes TRA documentation, malware scan reports, and relevant policies. | IT Responder |  |  |  | 5.3 | 5.3.2.1 | 80.2 | 5.3.2.1.b | 31.6 | Quarterly | Open
ACT | Conduct malware scans at the defined frequency & Keep records of all scans, including dates, scope, tools used, and findings | IT Responder |  |  |  | 5.3 | 5.3.2.1 | 80.3 | 5.3.2.1.b | 31.7 | Quarterly | Open
PLAN | Create policies that govern the use of removable media. Include guidelines on what types of media are allowed and under what circumstances | IT Responder |  |  |  | 5.3 | 5.3.3 | 81 | 5.3.3.a | 31.8 | Annual | Open
DO | Implement technical controls that enforce these policies, such as disabling USB ports or allowing only approved devices | IT Responder |  |  |  | 5.3 | 5.3.3 | 81.1 | 5.3.3.b | 31.9 | Annual | Open
DO | Apply hardening techniques to operating systems and applications to minimize vulnerabilities that could be exploited via malware on removable media. | IT Responder |  |  |  | 5.3 | 5.3.3 | 81.2 | 5.3.3.b | 32 | Annual | Open
CHECK | Ensure that the anti-malware solutions log all activities related to removable media, including scan results and any detected actions. | IT Responder |  |  |  | 5.3 | 5.3.3 | 81.3 | 5.3.3.c | 32.1 | Annual | Open
CHECK | Implement a process for regular review of these logs to identify and respond to potential threats | IT Responder |  |  |  | 5.3 | 5.3.3 | 81.4 | 5.3.3.c | 32.2 | Annual | Open
CHECK | Conduct periodic tests to ensure the anti-malware solutions are effectively scanning and detecting threats on removable media. | IT Responder |  |  |  | 5.3 | 5.3.3 | 81.5 | 5.3.3.a | 32.3 | Annual | Open
ACT | Conduct regular training sessions to educate employees about the risks associated with removable media and the organization’s policies | Overseer |  |  |  | 5.3 | 5.3.3 | 81.6 | 5.3.3.b | 32.4 | Annual | Open
ACT | Prepare an evidence including configurations, logs, and scan results regarding removable media, and training materials. | Overseer |  |  |  | 5.3 | 5.3.3 | 81.7 | 5.3.3.c | 32.5 | Annual | Open
PLAN | Develop and maintain policies and procedures that document the processes for log generation, retention, and analysis | IT Responder |  |  |  | 5.3 | 5.3.4 | 82 | 5.3.4 | 32.6 | Annual | Open
DO | Ensure that the anti-malware solutions deployed within the organization’s network have logging capabilities enabled | IT Responder |  |  |  | 5.3 | 5.3.4 | 82.1 | 5.3.4 | 32.7 | Annual | Open
DO | Verify that all systems that are part of the cardholder data environment (CDE) and connected systems are covered by anti-malware with enabled logging. | IT Responder |  |  |  | 5.3 | 5.3.4 | 82.2 | 5.3.4 | 32.8 | Annual | Open
DO | Implement procedures for regularly reviewing the anti-malware logs to identify and respond to potential security incidents. | IT Responder |  |  |  | 5.3 | 5.3.4 | 82.3 | 5.3.4 | 32.9 | Annual | Open
CHECK | Regularly test the effectiveness of the anti-malware solutions and log management processes through internal audits | IT Responder |  |  |  | 5.3 | 5.3.4 | 82.4 | 5.3.4 | 33 | Annual | Open
ACT | Store securely Anti-malware logs, with integrity controls to prevent tampering or deletion.for at least 1 year, with a minimum of Quarterly logs immediately available | IT Responder |  |  |  | 5.3 | 5.3.4 | 82.5 | 5.3.4 | 33.1 | Annual | Open
ACT | Collect and maintain evidence for compliance verification, such as screenshots, configuration files, and logs | Overseer |  |  |  | 5.3 | 5.3.4 | 82.6 | 5.3.4 | 33.2 | Annual | Open
ACT | Incorporate log data into the organization’s incident response plan to aid in the investigation and response to malware incidents. | Overseer |  |  |  | 5.3 | 5.3.4 | 82.7 | 5.3.4 | 33.3 | Annual | Open
PLAN | Establish a clear process for managing and authorizing requests to disable or alter anti-malware mechanisms | IT Responder |  |  |  | 5.3 | 5.3.5 | 83 | 5.3.5.a | 33.4 | Annual | Open | This process should include: A form or system for submitting requests. Criteria for evaluating and approving requests. Identification of management personnel authorized to approve such requests. A defined time frame for which the alteration or disablement is authorized.
PLAN | Develop and maintain an incident response plan to address scenarios where anti-malware mechanisms are found to be disabled without authorization | IT Responder |  |  |  | 5.3 | 5.3.5 | 83.1 | 5.3.5.a | 33.5 | Annual | Open
DO | Configure anti-malware solutions to Set permissions and privileges at a system level to ensure only authorized personnel can make changes. | IT Responder |  |  |  | 5.3 | 5.3.5 | 83.2 | 5.3.5.a | 33.6 | Annual | Open
DO | Configure anti-malware solutions to Set permissions and privileges at a system level to ensure only authorized personnel can make changes. | IT Responder |  |  |  | 5.3 | 5.3.5 | 83.3 | 5.3.5.a | 33.7 | Annual | Open
DO | Use centralized anti-malware management tools that allow control over anti-malware policies across all systems, preventing local alterations by users. | IT Responder |  |  |  | 5.3 | 5.3.5 | 83.4 | 5.3.5.a | 33.8 | Annual | Open
CHECK | Regularly review the use and effectiveness of anti-malware mechanisms and the process for managing exceptions | Overseer |  |  |  | 5.3 | 5.3.5 | 83.5 | 5.3.5.b | 33.9 | Annual | Open
ACT | Maintain logs of all approved requests, including details of requestor, the reason, the specific period of authorization, and the actual time of alteration | IT Responder |  |  |  | 5.3 | 5.3.5 | 83.6 | 5.3.5.b | 34 | Annual | Open
PLAN | Document implemented processes and mechanisms for Deployment of Anti-Phishing Controls | IT Responder |  |  |  | 5.4 | 5.4.1 | 84 | 5.4.1 | 34.1 | Annual | Open
DO | Implement solutions such as Domain-based Message Authentication, Reporting & Conformance (DMARC), Sender Policy Framework (SPF), & Domain Keys Identified Mail (DKIM). | IT Responder |  |  |  | 5.4 | 5.4.1 | 84.1 | 5.4.1 | 34.2 | Annual | Open
DO | Install Server-Side Anti-Malware and Link Scrubbers to analyze and sanitize URLs in emails, preventing personnel from accessing malicious sites. | IT Responder |  |  |  | 5.4 | 5.4.1 | 84.2 | 5.4.1 | 34.3 | Annual | Open
CHECK | Regularly review and update the anti-phishing controls to ensure they are effective against evolving phishing techniques. | IT Leaders |  |  |  | 5.4 | 5.4.1 | 84.3 | 5.4.1 | 34.4 | Annual | Open
ACT | Conduct Regular Training and Awareness Programs for personnel to recognize and report phishing emails & enhance the effectiveness of the anti-phishing strategy. | IT Responder |  |  |  | 5.4 | 5.4.1 | 84.4 | 5.4.1 | 34.5 | Annual | Open
ACT | Engage with External Resources for Information and Best Practices on defending against phishing attacks. | IT Responder |  |  |  | 5.4 | 5.4.1 | 84.5 | 5.4.1 | 34.6 | Annual | Open | Consult resources such as the National Cyber Security Centre and the US Cybersecurity & Infrastructure Security Agency for additional information and best practices on defending against phishing attacks
PLAN | Establish policies and procedures for managing payment page scripts, how scripts are authorized, how integrity is assured, and how the inventory is maintained. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85 | 6.4.3.a | 34.7 | Annual | Open
DO | Implement process to confirm that each script is authorized, Manual or Automated reviews to ensure only necessary & secure scripts are used. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.1 | 6.4.3.a | 34.8 | Annual | Open
DO | Use mechanisms like Sub-resource Integrity (SRI) which allows the browser to verify that a script hasn't been altered | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.2 | 6.4.3.a | 34.9 | Annual | Open
DO | Implement Content Security Policy (CSP) to restrict script sources and prevent data exfiltration. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.3 | 6.4.3.a | 35 | Annual | Open
DO | Develop and maintain an up-to-date inventory of all scripts, that should include details about each script’s purpose and justification for its necessity. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.4 | 6.4.3.a | 35.1 | Annual | Open
CHECK | Utilize monitoring tools to detect unauthorized changes to scripts or the introduction of new, unauthorized scripts. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.5 | 6.4.3.b | 35.2 | Quarterly | Open
CHECK | Conduct regular SOP audits to verify that scripts are being managed according to the defined policies and procedures. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.6 | 6.4.3.b | 35.3 | Quarterly | Open
ACT | Use CSP to control the sources from which scripts can be loaded and to restrict where data can be sent, thus enhancing the security of payment pages | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.7 | 6.4.3.b | 35.4 | Annual | Open
ACT | Using inline frames for payment pages, restrict where the payment page can be loaded from to prevent unauthorized content substitution. | IT Responder |  |  |  | 6.4 | 6.4.3 | 85.8 | 6.4.3.b | 35.5 | Annual | Open
ACT | Keep detailed records of the authorization, integrity checks, and inventory updates for each script. | IT Leaders |  |  |  | 6.4 | 6.4.3 | 85.9 | 6.4.3.b | 35.6 | Annual | Open
PLAN | Develop and enforce a policy that mandates the assignment of a unique ID to each user, that mandates sharing of user IDs is strictly prohibited. | IT Responder |  |  |  | 8.2 | 8.2.1 | 86 | 8.2.1.a | 35.7 | Annual | Open
DO | Assign a unique ID to each new user, & Ensure that this ID is distinct and not recycled from previous users. | IT Responder |  |  |  | 8.2 | 8.2.1 | 86.1 | 8.2.1.a | 35.8 | Annual | Open
DO | Implement an access control system that requires unique user IDs for authentication, & handle the addition, modification, and deletion of user accounts efficiently. | IT Responder |  |  |  | 8.2 | 8.2.1 | 86.2 | 8.2.1.a | 35.9 | Annual | Open
CHECK | Conduct regular audits of user IDs and access logs to ensure that audit logs record activities with the specific unique ID of the user who performed each action. | IT Responder |  |  |  | 8.2 | 8.2.1 | 86.3 | 8.2.1.b | 36 | Quarterly | Open
ACT | Include Point-of-Sale Exemption stating that user accounts within point-of-sale terminals access only one card number at a time for a single transaction. | IT Leaders |  |  |  | 8.2 | 8.2.1 | 86.4 | 8.2.1.b | 36.1 | Annual | Open
ACT | Include IRP procedures to address any violations in reference to shared IDs or unauthorized access. | IT Responder |  |  |  | 8.2 | 8.2.1 | 86.5 | 8.2.1.a | 36.2 | Annual | Open
PLAN | Create a policy that explicitly states that group, shared, or generic accounts are to be used only in Well-defined exceptional circumstances | IT Responder |  |  |  | 8.2 | 8.2.2 | 87